## Slide 1: SALURBAL Portal Update
Ran Li, Jessica Uruchima
10-02-2023

## Slide 2: Overview
Infrastructure Updates
  Data/Codebook Renovations
  Spatial Data + Admin Data Integration
Website Updates
  City Selection
  Spatial Pages
  Outputs Pages
  Feedback streamline
Next Steps

## Slide 3: Data/Codebook Renovations
25 datasets with completed renovation
17 datasets in the final stage of codebook validation
  Working with BEC team to finalize several datasets
7 datasets pending renovation
Priority datasets have all been renovated

## Slide 4: Spatial Renovations
Steve and his GIS team have been renovating spatial datasets and boundaries
  Operationalizing various boundary types e.g. NoIsland
  Embed metadata within geodatabases
Collaborating with renovation team to integrate modern spatial data storage into the SALURBAL system
  ESRI Geodatabase -> XML -> SALURBAL Data Infrastructure -> Portal

## Slide 5: Admin data integration
  worked with Fer’s publication tracking sheet of publication with PMID/PMCID
  Utilize PMCID to pull metadata from Pubmed API
  Cleaned up results (basic standardization, as well as AI summaries of abstracts for front-end)
  Overall structure tracking of project-related metadata in addition to data-data is really important work!

## Slide 6: Website: City selection scrolly
    English/Spanish finalized
    Portuguese pending BR team review
    Links:
      English: https://drexel-uhc.github.io/salurbal-city-selection-scrolly/
      Spanish: https://drexel-uhc.github.io/salurbal-city-selection-scrolly-spanish/
      Portuguese (in progress): https://dashing-choux-141b02.netlify.app/?review=true

## Slide 7: Website: Spatial Pages
    Link: https://wonderful-moss-0f45f310f-393.eastus2.azurestaticapps.net/data/spatial?review=true
    Create pages to display key spatial information
    Create metadata pages for spatial metadata

## Slide 8: Website: Outputs
    Link: https://wonderful-moss-0f45f310f-393.eastus2.azurestaticapps.net/outputs?review=true
      Catalog: https://wonderful-moss-0f45f310f-393.eastus2.azurestaticapps.net/outputs?review=true
      Publications: https://wonderful-moss-0f45f310f-393.eastus2.azurestaticapps.net/outputs/publications?review=true
      Interactives (Tools): https://wonderful-moss-0f45f310f-393.eastus2.azurestaticapps.net/outputs/interactives?review=true
    A /outputs landing page including some featured pieces of content and links to other outputs pages
    /outputs/catalog is a search interface to access machine actionable SALURBAL outputs. Note that it is limited to current metadata we have. The more metadata we collect and desiginig better ways to collect them leads to richer metadata and thus great accessiblity.
    Then individual pages designed to describe and highlight SALURBAL outputs
      /outputs/publications
      /outputs/interactives
      others are placeholders for other things, policy evals, events … etc

## Slide 9: Website: Outputs (discussion)
    Discussion what do we want to include in the release:
      Option 1 (min): Just the interactives page (as we had in pre-release)
      Option 2 (max): Include outputs, outputs-catalog, publications, interactives after polishing
        What do we need to polish?
          Ontology
          Language
          UiUx (filters, searches) more polished ui
      Option 3: less polishing restrict to readyish things.
        Publications only
        Send Outputs catalog to DMC for feedback then decide.

## Slide 10: Website: Internal Feedback streamlining
Link:
  Stable Portal Review Link: https://wonderful-moss-0f45f310f-393.eastus2.azurestaticapps.net/?review=true
Goal:
  reduce burden of giving website related feedback
  Increase rate of iteration

## Slide 11: Next steps
  Mid November release
  October
    back-end: Wrap up renovations
    front-end: Clear up metadata issues post renovation
    Plan for future:
      Refresh documentation (https://drexel-uhc.github.io/salurbal-fair-renovations/) for CODATA
      Develop a data/metadata ingestion pipeline/protocol for new datasets
      Continue collaborating with GIS team on metadata and data integrations